## Event Checklist
Mount Calvary African Methodist Episcopal Church
Rev. Bobby B Cox, Jr – Pastor
Rev. Angie Crawford-Cox – 1st Lady
ANNUAL DAYS/SPECIAL EVENT & ACTIVITIES CHECKLIST
| Annual Day/Ministry Event: |  |  | Event Date:
ACTIVITY |  | ASSIGNED TO (Name of Individual) | DUE DATE (Months/Days prior to event) |  | DATE COMPLETED (or date to be completed by)
I. | Getting Started
Select Committee Members
Choose Chairperson
| Reserve Date on Church Calendar |  | 6 - 12 months - Annual Days 3 - 6 months - all others
| Reserve Facility/Room/Area |  | 3 - 6 months
| Guest Speaker/Musician/etc. (Get approval from Pastor) |  | At least 90 days
| Develop Proposal and Submit to Commission |  | At least 90 days
• Activities (Complete proposal for each activity)
• Budget
• Timeliness
• Sub-committees
| Final Approval (Cabinet) |  | Approval Response within 14 days of receipt
| Check Voucher Request |  | Within 7 - 10 days prior to the date the check is required
II. | Publicity (Contact Church Office)
| Design and order posters/flyers |  | 45 days
| Email Blasts/Church Website |  | 30 days
| Announcement in Bulletin |  | 30 days
| Reserve Church Bulletin Board |  | 30 days
| Reserve Display Tables |  | 30 days
| Special Bulletin Cover (if applicable) |  | 30 days
III. | Order of Service (Require Pastor's Approval)
| Pulpit Participants Assignment |  | 14 days
| # of Presentations ____ |  | 14 days
| Litany (if applicable) |  | 14 days
IV. | Other Needs (if applicable)
For Speaker:(Contact Church Office)
| Honorarium |  | 30 days
| Transportation-Hotel |  | 30 days
| Gift Basket-Hotel |  | 30 days
| Armor Bearer |  | 30 days
| Special Requirements |  | 30 days
Church Support Ministries:
| Musicians/Choir/Dancers/Drama |  | 60 days
| Culinary (food/refreshments) |  | 30 days
| Special set-up or equipment |  | 30 days
| Security |  | 30 days
| Trustee (Access to facility/set-up/clean-up) |  | 30 days
| Ushers |  | 30 days
Other:
| Gifts (Pastor, Executive Minister, Honoree, etc.) |  | 14 days
| Handout/give-away/souvenir |  | 14 days

## Proposal (hidden)
Mount Calvary African Methodist Episcopal Church
Rev. Bobby B Cox, Jr – Pastor
Rev. Angie Crawford-Cox – 1st Lady
SPECIAL EVENT OR ACTIVITY PROPOSAL FORM
(To be Submitted 90 Days in Advance of Event Date to Quiana Johnson)
EVENT: _______________________________________________ |  | DATE(S)
PLACE/ROOM(S): ______________________________________ |  | TIME(S)
OBJECTIVE/PURPOSE: _______________________________________________________________________
PERSON(S) RESPONSIBLE (Name & Number):
OTHER MINISTRIES INVOLVED:
PROGRAM FOR: (Circle) | LOCAL CHURCH | DISTRICT | CONFERENCE
TYPE OF EVENT: (Circle) | SPIRITUALLY | FUND RAISER
SPREAKER REQUIRED: (Circle) | YES | NO
BUDGET INFORMATION
Estimated cost: $____________________________ |  | Estimated Income: $
Estimated Cost Breakdown
(a) Food $
(b) Publicity $
(c) Decoration $
(d) Room Rental $
(e) Speaker Honorarium $
Ministry Head Signature |  | Date
Commission's Signature |  | Date Received
Cabinet's Decision: (Circle) Approval / Disapproval |  | Placed on Church Calendar: Yes / No
Pastor's SIGNATURE |  | DATE
Pastor's COMMENTS:

## Check Request & Receipt Turn-in
Mount Calvary African Methodist Episcopal Church
Rev. Bobby B Cox, Jr – Pastor
DISBURSEMENT VOUCHER / CHECK REQUEST
Date: |  | Ministry/Organization:
Amount Requested: $ _________________
Church does not reimburse for taxes. Attach receipts if applicable.
Payable to:
Description/Purpose:
Requested by: |  |  | Payment Request Date:
There is a 7 - 10 day turn-around for payment.
| Ministry President's Signature |  | Ministry Treasurer's Signature
Cabinet Member's Signature
Mount Calvary African Methodist Episcopal Church
Rev. Bobby B Cox, Jr – Pastor
RECEIPT TURN-IN FORM
Date: ____________________ |  | Ministry/Organization:
Amount Initially Received: $______________ |  | Amount turned Back In: $_____________
Are Receipts attached? ______________ |  | If no, why not?
Amount of Personal Funds Used: $____________________
Payable to: (if Applicable)
| Ministry President's Signature |  | Ministry Treasurer's Signature
Cabinet Member's Signature (if check needed)

## Announcement Request
Mount Calvary African Methodist Episcopal Church
ANNOUNCEMENT REQUEST FORM
Submission Guidelines - Bulletin submissions require 2 week notification with information detailed below. Special bulletin cover and flyer designs require 6 week notice to the Communications Ministry.
Date of Request: ______________________________ |  |  | Announcement Dates:
Requestor: ____________________________ |  |  | Ministry/Organization:
Phone #: ______________________________ |  | Email: ________________________
Type of Advertisement:
Bulletin/Program | Pulpit | Bulletin Board | Flyer | Website
Information for announcement: WRITE LEGIBALLY (or attach flyer/poster)
Organization President's Signature |  |  | Date
Church Office: (Circle) Approval / Disapproval
Date

## Pulpit Participants
Mount Calvary African Methodist Episcopal Church
PULPIT PARTICIPANT ASSIGNMENTS
Annual Day/Ministry Event: ___________________________________________________________ |  |  | Event Date: _________________
8:00am Service | ASSIGNED TO (Name of Individual) | 11:00am Service | ASSIGNED TO (Name of Individual)
PRESIDING |  | PRESIDING
INVOCATION |  | INVOCATION
SCRIPTURE |  | SCRIPTURE
THE OCCASION/LITANY (If Applicable) |  | THE OCCASION/LITANY (If Applicable)
WELCOME |  | WELCOME
PRESENTATIONS |  | PRESENTATIONS
INTRO OF THE PREACHER |  | INTRO OF THE PREACHER
Organization President/Chairperson's Signature |  | Date
Pastor's Approval |  | Date

## Evaluation Sheet
Mount Calvary African Methodist Episcopal Church
SPECIAL EVENT OR ACTIVITY EVALUATION SHEET
(To be Submitted 2 weeks After the Event with Committee Report)
NAME OF EVENT: _________________________________________________________________
DATE EVENT TOOK PLACE: _______________________________________________________
WHAT WAS YOUR GENERAL IMPRESSION OF THE EVENT?
DO YOU THINK THE GOALS FOR THIS EVENT WERE ACHIEVED? WHY OR WHY NOT?
WHAT CHANGES WOULD YOU SUGGEST BE MADE IN TE FUTURE?
DO YOU RECOMMEND THIS EVENT TO BE CONTINUED? YES or NO
OTHER COMMENTS:
Organization President's Signature | Date

## Committee Report
Mount Calvary African Methodist Episcopal Church
SPECIAL EVENT OR ACTIVITY
COMMITTEE REPORT
(To be Submitted 2 weeks After the Event with Evaluation Sheet)
NAME OF EVENT: _________________________________________________________________
DATE EVENT TOOK PLACE: _______________________________________________________
Please give an overview of how the event/activity went; include any goals and objective that were met.
Total Income: (If applicable) | $
Total Expenses: (If applicable) | $
Net Income: (If applicable) | $
Organization President's Signature |  | Date